## Investment
Investment |  |  | All prices are in US Dollars
Below you will find the costs of our web development service:
Name | Price |  | Qty |  | Sub-Total
Website Design (Hrs) | 20 |  | 35 |  | 700
Hosting & Security Certificate (Annual) | 50 |  | 1 |  | 50
Domain (Annual) .com.mx | 50 |  | 1 |  | 50
SEO, Analytics | 25 |  | 1 |  | 25
Copywriting | 50 |  | 1 |  | 50
Maintenance (Annual - 3 months free) | 25 |  | 9 |  | 225
Updates to pages
|  |  |  | Sub-total | 1100
|  |  |  | TAX (16%) | 176
|  |  |  | Total | 1276
Terms & Conditions
The current proposal is valid until March 31st, 2022. A 50% upfront will be due 7 days after the
acceptance of the current proposal. All assets must be delivered within 3 days of the acceptance of the current proposal.
The proposal only includes web design, hosting, domian name, anaylitics, copywriting and mantainance. Other services such
as adding pluggins must be purchased separately.
Acceptance
The quotation is subject to mutually accepting the terms and conditions and will require a 50%
upfront payment and 50% upon completion of the project.
Client |  | Pablo Salvatella
Date: |  | Date:
Name: |  | Pablo Salvatella

## Timetable
Timetable
April
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Brief
Complete
Design
Mockups
Colors & Fonts
Sections
Content Edition
Structure
Wireframe Prototype
Site Architecture
Development
Content Upload
Tests
Client Feedback
Production
Hosting
Configuration
Delivery